CuddlePirates × Volta

Master Plan — Strategy, Scope & Timeline to the Q3 2026 Pitch

Author: Andy Rose

Created: 2026-05-23

Horizon: Now → Q3 2026 founding-principals pitch (feature/series = long-horizon)

Cadence: ~15–25 hrs/week, solo, alongside the Lightspeed LA day job

Scope: CuddlePirates (creative target) + Volta (production pipeline). Bear Suit Man is intentionally out of scope.

# 1. The relationship in one sentence

Volta is the pipeline; CuddlePirates is the proof. Volta is an AI-assisted virtual-production pipeline (Concept → Mesh → Rig → Anim → FX → Comp → Export) built as a real Python CLI. CuddlePirates is the first demo IP, and its only near-term job is to produce a 30–60-second vertical slice that proves Volta works — the centerpiece of a Q3 2026 pitch to four founding equity principals.

# 2. Scope & target of each project

## CuddlePirates — the creative target

| Dimension | Definition |
| --- | --- |
| Near-term deliverable | A 30–60s rendered vertical slice: the infiltration sequence from the pilot (The Sock-topuss). |
| Long-horizon ambition | A full CGI feature/series — deferred until the studio exists and is funded. Not on the critical path. |
| Style (locked) | Stylized painterly plush / storybook. NOT photoreal. |
| Hero assets for the slice | 2 hero characters (Sir Fuzzy Drake + 1 TBD) · 1 hero environment (Juniper's bedroom) · 1 hero prop (The Fluffy Dutchman). |
| Creative canon | Round 2 locked (30/30 questions). IP, tone, beat sequence all defined. |
| Open creative items | G5 IP ownership (Andy's call) · 2nd hero TBD · story-bible canon still placeholder · K3 rig conflict resolved toward custom stylized rigs. |

## Volta — the production pipeline

| Dimension | Definition |
| --- | --- |
| What it is | A single-CLI orchestration layer that makes a 5-person boutique operate like a 50-person pipeline: local-first (M6), AI-augmented (not AI-driven), approval-gated, cost-visible, reusable. |
| Near-term target | Take the CuddlePirates vertical slice end-to-end — and emit real per-stage cost telemetry. |
| Built today | SQLite catalog (tiers/provenance/approval gates), CLI (~841 lines), QA validators, ATLAS bridge sync, basic ComfyUI + Meshy clients, FFmpeg/social export, BVH mocap ingest, HIK templates. |
| Phase-2 stubs (block reel) | Full-pipeline orchestration (volta run / runner.py), film export via UE5 Movie Render Queue → EXR/ProRes, auto-rig, Cascadeur mocap cleanup. |
| Long-horizon target | Internal-only product; multi-tenancy/billing deferred. External licensing only after the pipeline is proven. |

## The central tension to resolve

The pipeline cannot yet render the very deliverable it exists to prove. Film export is stubbed, end-to-end orchestration is stubbed, and the reel is “in production.” The deck is written in the present tense while the rendering path doesn’t run end-to-end. Closing that gap is the whole game between now and Q3.

# 3. Goals

## Primary goal (this plan)

Render the CuddlePirates vertical slice through Volta, capture real cost telemetry, finalize the deck, and pitch the four principals in Q3 2026.

## Supporting goals

- Volta: Make the reel-critical path real — orchestration, stylized-rig path (Concept→Mesh→UE5), film export (MRQ→EXR + MP4 dailies), and stage-cost telemetry surfaced to the deck.

- CuddlePirates: Lock remaining creative (G5 ownership, 2nd hero, pilot-slice story-bible canon) and build the four hero assets through to HERO tier.

- Pitch: Finalize the deck with real numbers + rendered reel + principal bios + I3/I4 answers; run Wave 1 (Producer, Artist, Editor) then Wave 2 (VP Supervisor).

## Long-horizon goal (off critical path)

Convert a successful pitch into a funded boutique studio that produces the CuddlePirates feature/series — pipeline as the asset, IP as the proof.

## Definition of done (pitch-ready)

- 30–60s reel rendered at 4K (EXR master + MP4 daily), with scratch-or-locked audio.

- volta run produces the slice end-to-end and logs per-stage cost; the cost-model slide uses real numbers, not placeholders.

- Deck Wave-1 sections complete with bios + I4 NLE answer; reel embedded.

- A documented fallback (beat board + partial reel) exists in case rendering slips.

# 4. The master plan — phased, with timeline

Today is 2026-05-23. Target Wave-1 pitch: week of Sept 7, 2026 (~15 weeks out). Because the work is solo, engineering capability and creative build interleave rather than fully parallelize: each pipeline stage must work before the creative asset for that stage can flow through it.

| Phase | Window | Focus |
| --- | --- | --- |
| 0 — Decisions & foundation | Now → ~Jun 1 | Lock G5 ownership; pick 2nd hero; send I3/I4 outreach; per-project catalog migration + CuddlePirates production board. |
| 1 — Pipeline-to-reel (CRITICAL) | Jun 1 → Jun 28 | runner.py orchestrator; film export MRQ→EXR + MP4 dailies; stylized-rig path; HERO approval gate; stage-cost telemetry. |
| 2 — Hero asset build | Jun 15 → Jul 19 | Sir Fuzzy Drake + 2nd hero to HERO; Juniper's bedroom env; Fluffy Dutchman prop; story-bible canon for the slice. |
| 3 — Vertical slice production | Jul 13 → Aug 9 | Block infiltration sequence in UE5 Sequencer; ANIM (ragdoll/freeze); cloth FX; two-light-source COMP; locked cut + scratch audio. |
| 4 — Render, finish & telemetry | Aug 3 → Aug 30 | volta run → 4K EXR + MP4 dailies; editorial + sound stems + color; capture real telemetry → cost-model slide. |
| 5 — Pitch finalization | Aug 24 → Sep 13 | Update deck (reel + real numbers + bios + I4); Wave 1 pitch (Producer/Artist/Editor); schedule Wave 2 (VP Supervisor). |

## Phase detail

Phase 0 — Decisions & foundation lock · Now → ~Jun 1 (Week 0–1)

- Resolve G5 IP ownership (docs recommend Andy solo — keeps footage licensable without principal approval).

- Choose the 2nd hero character from the roster.

- Send I3/I4 outreach to principals (VP Supervisor gold-standard pipeline; FX Editor NLE + round-trip format).

- Stand up creative tracking: scaffold the CuddlePirates production board + finish per-project catalog migration (volta init).

- Exit criteria: ownership decided, 2nd hero named, principal questions sent, CuddlePirates catalog live.

Phase 1 — Pipeline-to-reel engineering · Jun 1 → Jun 28 (CRITICAL PATH)

- Build the runner.py orchestrator (volta run UID): archive-on-rerun + auto-cascade across stages.

- Implement film export: UE5 Movie Render Queue → 4K EXR + ProRes, plus the always-on MP4 dailies lane.

- Wire the stylized-rig path: Concept (MJ) → Meshy mesh → Blender cleanup → custom UE5 stylized rig (no MetaHuman for heroes).

- Enforce approval gate for tier=HERO (volta approve / reject).

- Add stage-cost telemetry (Meshy credits + GPU-seconds + compute hours) surfaced to a deck-quotable summary.

- Exit criteria: a throwaway test asset goes ingest→export and prints real per-stage cost.

Phase 2 — Hero asset build · Jun 15 → Jul 19 (overlaps Phase 1)

- Sir Fuzzy Drake through the full promotion path to HERO (cloth/plush sim baked at rig).

- 2nd hero character through the same path.

- Juniper's bedroom environment (Concept → Mesh → handcrafted UE5 lookdev — no pure PCG).

- The Fluffy Dutchman prop (pillowcase hull cloth sim, legs underneath).

- Promote story-bible canon for the pilot slice from placeholder → locked.

- Exit criteria: all four hero assets at HERO tier with approvals + cost logged.

Phase 3 — Vertical slice production · Jul 13 → Aug 9

- Block the 30–60s infiltration sequence in UE5 Sequencer (window drop → hall-light freeze → bed landing → ragdoll acrobatics → bow).

- ANIM: silent physical-comedy timing; full-body ragdoll response to the simulated sound/light event.

- FX: cloth/soft-body on pajamas, pillowcase hull, sails/rigging; light dust/atmosphere.

- COMP: two-light-source design (warm hall light = threat, cool moonlight = safe) — the comedy beat is a lighting cut.

- Exit criteria: locked cut (playblast-approved), scratch audio in place.

Phase 4 — Render, finish & telemetry capture · Aug 3 → Aug 30

- Render via volta run → 4K EXR master + MP4 dailies (the real test of Phase 1).

- Editorial assembly + sound pass (VO/score/SFX as discrete stems) + color.

- Capture real stage telemetry from the production run → replace every placeholder in the cost-model slide.

- Exit criteria: delivered reel + a real cost table.

Phase 5 — Pitch finalization & delivery · Aug 24 → Sep 13

- Update deck: embed reel, drop in real telemetry, add principal bios, answer I4 in the EXPORT slide.

- Wave 1 pitch: Producer + Artist + Editor (already aware of CuddlePirates).

- Wave 2 pitch: Senior VP Supervisor, after I3 is answered and Wave 1 lands.

- Exit criteria: all three Wave-1 pitches delivered; Wave-2 scheduled.

Long-horizon track (post-pitch, off critical path)

Feature/series scoping, studio formation, funding model, and series-bible expansion — planned only once principals are signed and the pipeline is proven.

# 5. Critical path & dependencies

The hard gate: film export + runner.py (Phase 1) must work before Phase 4 can render. If Phase 1 slips, everything downstream slips. Treat Phase 1 as the project’s spine.

Phase 0 decisions ─┬─> Phase 1 pipeline engineering ──┐

│                                  ├─> Phase 4 render

└─> Phase 2 hero assets ─> Phase 3 ─┘        └─> Phase 5 pitch

# 6. Risks & mitigations

| Risk | Likelihood | Mitigation |
| --- | --- | --- |
| Phase-1 engineering (MRQ export, orchestration) overruns | High | Start Phase 1 immediately; timebox; deck supports a beat-board fallback if the reel isn't fully rendered. |
| Solo bandwidth collides with day-job crunch | Med-High | Sprint-based milestones; keep the slice tiny (1 env, 2 chars, 1 prop, 30–60s); cut to 30s if needed. |
| Telemetry never materializes → cost slide stays placeholder | Medium | Bake telemetry capture into Phase 1 so it's automatic by Phase 4. |
| Style drift (AI fights the painterly look) | Medium | Lock style refs early; MetaHuman strictly a non-hero fallback seam per K3. |
| Principals unavailable in Q3 / scheduling | Medium | Send I3/I4 outreach in Phase 0; pre-book pitch windows. |

# 7. Immediate next actions (this week)

- Decide G5 IP ownership.

- Pick the 2nd hero character.

- Send I3 + I4 questions to the relevant principals.

- Run the per-project catalog migration and scaffold the CuddlePirates production board.

- Begin the runner.py + film-export spike (the Phase 1 spine).

This plan covers CuddlePirates + Volta only. Bear Suit Man, studio-business formation, and the long-horizon feature/series are explicitly off the near-term critical path.